Client Acquisition Game Plan

Date: 2025-12-10

Goal: 100 founding members

Timeline: End of Q1 2026 (aggressive) / End of Q2 2026 (realistic)

# 1. Passive/Automated Campaigns (Set and Forget)

## 1.1 Email Campaign → Targeted Nonprofits

Info needed:

Nonprofit name, EIN, contact email

Revenue ($500K-$5M)

NTEE code / sector

State

Foundation grant history (few/none = higher priority)

How to gather:

F990 database query (C3, C4 queries from Research Team output)

Enrich with contact emails via email address finding script

Platform: Email campaign script

## 1.2 Email Campaign → Grant Writing Firms

Info needed:

Firm name, website, contact email

Geographic focus

Client types they serve

Size (solo vs. team)

How to gather:

Web search: "grant writing consultant [state]"

LinkedIn search: "Grant Writer" + filter by location

GPA (Grant Professionals Association) directory

Platform: Email campaign script

## 1.3 Email Campaign → Capacity-Building Funders

Info needed:

Foundation name, EIN

Contact info (website, program officer if available)

Evidence they fund capacity building / nonprofit support

Typical grant size

How to gather:

F990 query: grant purpose ILIKE '%capacity%' OR '%nonprofit support%' OR '%technical assistance%'

Cross-reference with foundation websites

Platform: Email campaign script

## 1.4 Social Media / LinkedIn Posts

Info needed:

None — just post

How to gather:

N/A

Action: Post on personal LinkedIn, Facebook announcing service

# 2. Active Network Mining (High-Value Research)

## 2.1 Beta Clients' Funders → Their Other Grantees

Info needed:

List of foundations that funded each beta client

Other nonprofits those foundations have funded

Contact info for those nonprofits

How to gather:

F990 query: Find foundation EINs from beta client grant history

F990 query: Find all other grantees of those foundations

Filter to similar size/sector

Outreach angle: "We helped [beta client] — [Foundation X] also funds you, thought you might benefit"

## 2.2 LinkedIn Connections Audit

Info needed:

Which of your connections work at nonprofits

Their role (ED, Development Director = decision maker)

Org size and sector

How to gather:

LinkedIn: Export connections or manually review

Filter by title: "Executive Director," "Development," "Grants Manager"

Action: Warm outreach to qualified connections

## 2.3 Friends & Family Nonprofit Connections

Info needed:

Who in your network works at or knows someone at a nonprofit

Their boss / decision maker name

Org name and what they do

How to gather:

Direct asks / texts

Already have some leads (mentioned bosses are interested)

Action: Ask for warm intros

## 2.4 Beta Client Warm Intro Asks

Info needed:

Who beta clients know (peer EDs, professional networks)

Which relationships are strong enough to ask

How to gather:

Direct ask in email/call: "Who else do you know that struggles with grant discovery?"

Review their LinkedIn connections

Action: Request 1-2 intros per beta client

# 3. High-Leverage Calls (Multiplier Targets)

## 3.1 Foundations That Fund Capacity Building

Info needed:

Foundation name, EIN

Program officer / contact

Evidence of capacity building or "nonprofit support" grantmaking

Geographic focus

Typical grant size

How to gather:

F990 query (same as 1.3)

Foundation websites for contact info

Pitch: "Fund TheGrantScout subscriptions for your grantees — multiply your impact"

## 3.2 Grant Writing Firms (Partnership)

Info needed:

Firm name, principal contact

Number of clients / client types

Current service offerings

Interest in referral or white-label arrangement

How to gather:

Same as 1.2

Discovery call to qualify

Pitch: "We handle discovery, you handle writing — referral fee or bundled service"

## 3.3 State Nonprofit Associations

Info needed:

Association name, state

Membership size

Training/webinar program (do they host external speakers?)

Contact for partnerships or programming

How to gather:

National Council of Nonprofits directory

Association websites → "Partner with us" or "Training" pages

Pitch: "Free webinar for your members on finding foundation funding"

## 3.4 Fiscal Sponsors

Info needed:

Organization name

Number of sponsored projects

Geographic/sector focus

Contact for partnerships

How to gather:

NNFS (National Network of Fiscal Sponsors) directory

Web search: "fiscal sponsor [state]"

Pitch: "Offer grant discovery to your sponsored projects — volume discount available"

# 4. Sponsor/Subsidy Angle (B2B Play)

## 4.1 Community Foundations

Info needed:

Foundation name, assets, geographic focus

Whether they have "nonprofit support" or "capacity building" programs

Program officer contact

How to gather:

F990 query: Large community foundations by assets

Foundation websites for program info

Pitch: "Fund 10 subscriptions for local nonprofits — $12K/year, we handle everything"

## 4.2 Corporate CSR Programs

Info needed:

Company name

CSR focus areas (nonprofit capacity, community development)

Contact / application process

How to gather:

Web search: "[Company] nonprofit support program"

Target: Tech companies, banks, large employers in your area

Pitch: "Sponsor grant discovery for nonprofits in your community"

## 4.3 Government / SBA Programs

Info needed:

Program name

Eligibility requirements

Whether they fund tools/services for nonprofits

Application process

How to gather:

Research Team deep-dive on SBDC, state nonprofit infrastructure programs

SAM.gov for relevant federal programs

Pitch: "Technical assistance tool for nonprofit capacity building"

# 5. Execution Priorities

## This Week

[ ] Run F990 queries for nonprofit targets (C3, C4)

[ ] Run F990 query for capacity-building funders

[ ] Audit LinkedIn connections for nonprofit contacts

[ ] Email 5 beta clients asking for 1 referral each

[ ] Text friends/family with nonprofit connections

[ ] Follow up with Terry/VetsBoats

[ ] Post on LinkedIn announcing service

## Next Week

[ ] Launch nonprofit email campaign (1,000 targets)

[ ] Launch grant writer email campaign (50 targets)

[ ] Call 10 capacity-building foundations (sponsor pitch)

[ ] Call 10 grant writing firms (partnership pitch)

[ ] Contact 3 state nonprofit associations (webinar pitch)

## Ongoing

[ ] 20 cold calls/day to prioritized list

[ ] 5 LinkedIn connections/day

[ ] Follow up all email responses within 24 hours

[ ] Track everything in spreadsheet

# 6. Conversion Math

| Channel | Volume | Response | Conversion | Clients |
| --- | --- | --- | --- | --- |
| Cold calls (targeted) | 2,000 | 6% interest | 33% close | 40 |
| LinkedIn outreach | 500 | 10% engage | 25% close | 12 |
| F990 email (nonprofits) | 5,000 | 1% respond | 20% close | 10 |
| Referrals (beta + network) | 30 | 50% intro | 40% close | 6 |
| Grant writer partnerships | 10 deals | — | 3 clients each | 30 |
| Foundation sponsors | 5 deals | — | 10 orgs each | 50 |
| Total Potential |  |  |  | 148 |

Foundation sponsors and grant writer partnerships are the multipliers. Direct outreach builds pipeline while partnerships scale.

# 7. Key Assets Ready

[x] Website complete

[x] Example report done

[x] Pricing set ($100/mo founding rate)

[x] F990 database queryable

[x] Email campaign script ready

[x] Email address finding script ready

[x] Beta client testimonials available

[ ] Sponsor pitch deck (1-pager)

[ ] Grant writer partnership proposal

*Document: SPEC_2025-12-10_client_acquisition_gameplan.md*