## Dashboard
| Goals | Due Date
1 | Generate and send 5 more beta reports | 2026-01-19
| Send VetsBoats their first report | 2026-01-19
| Call foundation leads back. | 2026-01-19
| Call 100 nonprofit prospects directly | 2026-01-19
| Migrate database to Supabase (for easier report generation) | 2026-01-19
| Consolidate report generation scripts/prompting | 2026-01-19
|  | Plans | Due Date
| Generate and send 5 more beta reports | Write up report on last nights run | 2026-01-20
| Generate and send 5 more beta reports | Analyze run and find identify matches for all 5 beta groups | 2026-01-20
| Generate and send 5 more beta reports | Build Test Harness | 2026-01-21
| Generate and send 5 more beta reports | Run test harness | 2026-01-21
| Generate and send 5 more beta reports | Finish Phase 4 for easy reports | 2026-01-20
| Migrate database to Supabase (for easier report generation) | Make supabase able to handle more data | 2026-01-21
| Migrate database to Supabase (for easier report generation) | Rerun import script (piece by piece version) | 2026-01-21
| Consolidate report generation scripts/prompting | Identify additional f990 data to import | 2026-01-22
| Consolidate report generation scripts/prompting | Run pipeline on 100 test nonprofits | 2026-01-23
| Consolidate report generation scripts/prompting | Make pipeline V4 | 2026-01-23
| Consolidate report generation scripts/prompting | Identify nonprofits to test on and call (from the foundation who said no) | 2026-01-20
| Call 100 nonprofit prospects directly | Call 20 nonprofits | 2026-01-20
| Call 100 nonprofit prospects directly | Call 30 nonprofits | 2026-01-21
| Call 100 nonprofit prospects directly | Call 20 nonprofits | 2026-01-22
| Call 100 nonprofit prospects directly | Call 30 nonprofits | 2026-01-23

## To Do
Date | Week Day | Priority | Goal | Task |  | Date Completed
2025-12-01 | Monday | 1 |  | Bullet list of report material options | Sales Prep | 2025-12-01
2025-12-01 | Monday | 1 |  | Email Miriam | Beta Testing | 2025-12-01
2025-12-01 | Monday | 1 |  | Review reports | Sales Prep | 2025-12-01
2025-12-01 | Monday | 2 |  | Message Terry | Sales | 2025-12-01
2025-12-01 | Monday | 3 |  | Email follow up to beta group 1 | Beta Testing | 2025-12-01
2025-12-01 | Monday | 4 |  | Make Beta Group 2 onboarding form (shorten questions and ask more about format of deliverable) | Beta Testing | 2025-12-01
2025-12-01 | Monday | 5 |  | Email new person from today | Beta Testing | 2025-12-01
2025-12-01 | Monday | 5 |  | Email person who filled out form | Beta Testing | 2025-12-01
2025-12-01 | Monday | 6 |  | Identify fields to include in F990 database | Product Development | 2025-12-01
2025-12-01 | Monday | 6 |  | Make report template | Sales Prep | 2025-12-01
2025-12-03 | Wednesday | 1 |  | Update Beta Leads Table | Beta Testing | 2025-12-03
2025-12-03 | Wednesday | 1.5 |  | Call BG1 | Beta Testing | 2025-12-03
2025-12-03 | Wednesday | 2 |  | Email Mariam | Beta Testing | 2025-12-03
2025-12-03 | Wednesday | 2 |  | Update onboarding form | Beta Testing | 2025-12-03
2025-12-03 | Wednesday | 3 |  | Synthesize BG1 round 1 findings | Sales Prep | 2025-12-03
2025-12-03 | Wednesday | 3 |  | What changes need to be made? | Sales Prep | 2025-12-03
2025-12-03 | Wednesday | 4 |  | Build F990 XLM import script and begin import | Product Development | 2025-12-03
2025-12-03 | Wednesday | 5 |  | Push website changes | Sales Prep | 2025-12-03
2025-12-04 | Thursday | 1 |  | Prep for meeting with Terry | Sales | 2025-12-04
2025-12-04 | Thursday | 1.5 |  | Meet with Terry | Sales | 2025-12-04
2025-12-04 | Thursday | 2 |  | Email last 2 BG1 nonprofits - no need to fill out form, just give me feedback | Beta Testing | 2025-12-04
2025-12-04 | Thursday | 4 |  | Check database import for completeness | Product Development | 2025-12-04
2025-12-04 | Thursday | 5 |  | Put cleaned up demo report on website | Sales Prep | 2025-12-04
2025-12-04 | Thursday | 6 |  | What questions need to be answered by BG1/BG2 and before making sales? | Sales | 2025-12-04
2025-12-04 | Thursday |  |  | Send follow up email to Terry |  | 2025-12-04
2025-12-05 | Friday | 1 |  | Fix database holes (phase 1) | Product Development | 2025-12-05
2025-12-05 | Friday | 1 |  | Enrich URLs column | Product Development | 2025-12-09
2025-12-05 | Friday | 1 |  | Enrich grants table recipient EINs | Product Development | 2025-12-09
2025-12-05 | Friday | 1.5 |  | Make last round of website edits | Sales Prep | 2025-12-09
2025-12-05 | Friday |  |  | Clean up folder structure | Product Development | 2025-12-05
2025-12-08 | Monday | 3 |  | Make and warm up thegrantscout.com emails
2025-12-08 | Monday | 3 |  | Make Linkedin and Social Media pages
2025-12-08 | Monday | 4 |  | Send out Insta/FB friend requests
2025-12-08 | Monday | 5 |  | Make and schedule Linkedin and Social Media posts for December
2025-12-09 | Tuesday |  |  | Make a privacy policy | Sales Prep | 2025-12-09
2025-12-10 | Wednesday | 1 |  | Follow up with Terry | Sales | 2025-12-10
2025-12-10 | Wednesday | 2 |  | Import the rest of the f990 data | Product Development | 2025-12-10
2025-12-10 | Wednesday | 2.1 |  | Enrich EINs | Product Development | 2025-12-10
2025-12-10 | Wednesday | 2.2 |  | Enrich URLs | Product Development | 2025-12-10
2025-12-10 | Wednesday | 2.3 |  | Build Dim tables | Product Development | 2025-12-11
2025-12-10 | Wednesday | 2.4 |  | Build calc tables | Product Development | 2025-12-11
2025-12-10 | Wednesday | 2.45 |  | Semantic Embedding
2025-12-10 | Wednesday | 2.5 |  | Build match tables | Product Development
2025-12-10 | Wednesday | 2.6 |  | Make and send BG1 V2 reports | Beta Group
2025-12-10 | Wednesday | 8 |  | Have the research team build a launch/outreach plan | Launch | 2025-12-10
2025-12-11 | Thursday | 1 |  | Send Jonathan Market Research | Accountability
2025-12-12 | Friday | 1 |  | Make Calls | Sales | 2025-12-12
2025-12-15 | Monday | 1.1 |  | Prep for meeting with Matt | Sales | 2025-12-12
2025-12-15 | Monday | 1.2 |  | Meet with Matt | Sales | 2025-12-12
2025-12-15 | Monday | 2.1 |  | Finish market research doc (and business plan doc?) | Accountability | 2025-12-15
2025-12-15 | Monday | 2.2 |  | Write email to Jonathan | Accountability | 2025-12-15
2025-12-15 | Monday | 2.3 |  | Send email to Jonathan | Accountability | 2025-12-15
2025-12-15 | Monday | 3.1 |  | Email Beta group about software updates and delays | Beta | 2025-12-15
2025-12-15 | Monday | 3.2 |  | Email Dan's friend a friendly hello | Sales | 2025-12-15
2025-12-15 | Monday | 4.1 |  | Update website to include yearly subscription option | Sales | 2025-12-15
2025-12-15 | Monday | 4.2 |  | Post on FB and Instagram | Sales | 2025-12-15
2025-12-15 | Monday | 5.1 |  | Semantic Embedding Phase 1 review | Product Development | 2025-12-15
2025-12-15 | Monday | 5.2 |  | Start Semantic Embedding Phase 2 | Product Development | 2025-12-15
2025-12-16 | Tuesday | 4.3 |  | Set up follow up email campaign | Sales | 2025-12-16
2025-12-16 | Tuesday | 4.5 |  | Call 4 Funders | Sales | 2025-12-16
2025-12-16 | Tuesday | 5.3 |  | Semantic Embedding Phase 2 review | Product Development | 2025-12-16
2025-12-16 | Tuesday | 5.4 |  | PGVector and migration | Product Development | 2025-12-16
2025-12-17 | Wednesday | 1.1 |  | Find emails/contact people at foundations |  | 2025-12-17
2025-12-17 | Wednesday | 1.2 |  | Call many foundations |  | 2025-12-17
2025-12-17 | Wednesday | 5.3 |  | Enrich EINs in Database
2025-12-17 | Wednesday | 5.6 |  | Fix Table of contents on formatter/report template |  | 2025-12-24
2025-12-18 | Thursday | 5.4 |  | Research algorithm |  | 2025-12-31
2025-12-18 | Thursday |  |  | Send Deb the list |  | 2025-12-18
2025-12-24 | Wednesday | 2.1 |  | Migrate DB to Mac |  | 2025-12-24
2025-12-24 | Wednesday | 2.2 |  | Update software to run on Mac |  | 2025-12-24
2025-12-24 | Wednesday |  |  | Improve site SEO |  | 2025-12-24
2025-12-24 | Wednesday |  |  | Make a bunch of linkedin posts |  | 2025-12-24
2025-12-24 | Wednesday |  |  | Set up GA4 for website traffic monitoring |  | 2025-12-24
2025-12-31 | Wednesday |  |  | Build Model v4 |  | 2025-12-31
2025-12-31 | Wednesday |  |  | Gather and clean call call list for Monday |  | 2025-12-31
2025-12-31 | Wednesday |  |  | Write script pipeline |  | 2025-12-31
2026-01-02 | Friday | 0.1 |  | Write todo list |  | 2026-01-02
2026-01-02 | Friday | 0.15 |  | Write down what I did over the break |  | 2026-01-02
2026-01-02 | Friday | 0.2 |  | Make plan for next week |  | 2026-01-02
2026-01-02 | Friday | 0.3 |  | Write report for Jonathan |  | 2026-01-02
2026-01-02 | Friday | 0.4 |  | Send Jonathan Report |  | 2026-01-02
2026-01-02 | Friday | 1.1 |  | Build and review all beta reports |  | 2026-01-02
2026-01-02 | Friday | 1.12 |  | Make foundation scraping skill file |  | 2026-01-02
2026-01-02 | Friday | 1.13 |  | Write script for email body writing
2026-01-02 | Friday | 1.2 |  | Review reports |  | 2026-01-02
2026-01-02 | Friday | 1.3 |  | Send reports
2026-01-02 | Friday | 2.1 |  | Review CRM build |  | 2026-01-02
2026-01-02 | Friday | 2.2 |  | Enrich CRM prospects as needed |  | 2026-01-02
2026-01-02 | Friday | 2.3 |  | Plan on who to call each day next week |  | 2026-01-02
2026-01-02 | Friday | 3.1 |  | Review week linkedin plan output |  | 2026-01-02
2026-01-02 | Friday | 3.2 |  | Review week 1 linkedin posts |  | 2026-01-02
2026-01-02 | Friday | 3.3 |  | Make a linkedin |  | 2026-01-02
2026-01-02 | Friday | 3.4 |  | Set my personal linkedin up as a creator |  | 2026-01-02
2026-01-02 | Friday | 3.6 |  | Launch automatic linkedin posting |  | 2026-01-02
2026-01-02 | Friday | 4.1 |  | Update Email campaign (messaging and people to reach out to)
2026-01-02 | Friday | 4.2 |  | Start nonprofit campaign
2026-01-02 | Friday | 4.3 |  | Warm up thegrantscout email campaign emails
2026-01-05 | Monday |  |  | Call Jesse Ostroff |  | 2026-01-05
2026-01-06 | Tuesday |  |  | research Alletta morris mcbean char.. |  | 2026-01-05
2026-01-06 | Tuesday |  |  | Call michele at oxford financial group (in the afternoon0
2026-01-06 | Tuesday |  |  | Email Maribel Cruz at seven acres foundation
2026-01-08 | Thursday |  |  | Fix SEO google problem | Marketing/Visibility | 2026-01-05
2026-01-08 | Thursday |  |  | Find east coast foundations | Sales Prep | 2026-01-08
2026-01-12 | Monday |  |  | Email Matt about payment | Direct Sales Actions | 2026-01-12
2026-01-13 | Tuesday | 3.2 |  | Respond to Margi/Melissa's email |  | 2026-01-13
2026-01-13 | Tuesday | 3.3 |  | Respond to Matts email |  | 2026-01-13
2026-01-14 | Wednesday |  |  | Call Grammy |  | 2026-01-14
2026-01-14 | Wednesday |  |  | Call Bethany |  | 2026-01-14
2026-01-14 | Wednesday |  |  | Call Braden |  | 2026-01-14
2026-01-14 | Wednesday |  |  | Send Braden Claude Code ClI startup guide |  | 2026-01-14
2026-01-15 | Thursday |  |  | Confirm Braden setup Claude Code CLI |  | 2026-01-15
2026-01-16 | Friday | 0.01 |  | Prep for call with Matt and Terry - Moneyball - Send teams link - List of deliverables in a report - List of similar nonprofits - List of target funders | Sales Prep | 2026-01-16
2026-01-16 | Friday | 0.1 |  | Call with Matt and Terry | Direct Sales | 2026-01-16
2026-01-16 | Friday | 3.3 |  | Write up report for last week - Jonathan, Bishop, Grammy | Planning & Accountability | 2026-12-19
2026-01-16 | Friday
2026-01-20 | Tuesday |  | Generate and send 5 more beta reports | Write up report on last nights run |  | 2026-01-20
2026-01-20 | Tuesday |  | Generate and send 5 more beta reports | Analyze run and find identify matches for all 5 beta groups |  | 2026-01-20
2026-01-20 | Tuesday |  | Generate and send 5 more beta reports | Finish Phase 4 for easy reports
2026-01-20 | Tuesday |  | Consolidate report generation scripts/prompting | Identify nonprofits to test on and call (from the foundation who said no)
2026-01-20 | Tuesday |  | Call 100 nonprofit prospects directly | Call 20 nonprofits
2026-01-21 | Wednesday |  | Generate and send 5 more beta reports | Build Test Harness
2026-01-21 | Wednesday |  | Generate and send 5 more beta reports | Run test harness
2026-01-21 | Wednesday |  | Migrate database to Supabase (for easier report generation) | Make supabase able to handle more data
2026-01-21 | Wednesday |  | Migrate database to Supabase (for easier report generation) | Rerun import script (piece by piece version)
2026-01-21 | Wednesday |  | Call 100 nonprofit prospects directly | Call 30 nonprofits
2026-01-22 | Thursday |  | Consolidate report generation scripts/prompting | Identify additional f990 data to import
2026-01-22 | Thursday |  | Call 100 nonprofit prospects directly | Call 20 nonprofits
2026-01-23 | Friday |  | Consolidate report generation scripts/prompting | Run pipeline on 100 test nonprofits
2026-01-23 | Friday |  | Consolidate report generation scripts/prompting | Make pipeline V4
2026-01-23 | Friday |  | Call 100 nonprofit prospects directly | Call 30 nonprofits
2026-02-02 | Monday |  |  | Warm up email addresses | Sales Prep
2026-02-25 | Wednesday |  |  | update TGS data dictionary
2026-02-26 | Thursday |  |  | Open the leads excel sheet and see who to follow up with? (afternoon activity
2026-02-26 | Thursday |  |  | How much time did we save Matt looking through websites to find out eligibility - add that to the website
2026-02-26 | Thursday |  |  | Put a more current example report on the website
2026-02-27 | Friday |  |  | Analyze VB report process
2026-02-27 | Friday |  |  | Make Matts March Report
2026-02-27 | Friday |  |  | Linkedin posts on Fridays
2026-02-27 | Friday |  |  | Learn about what kind of nonprofits we can work with now that we have section I data (public charities)
2026-02-27 | Friday |  |  | How does the I data impact our reports flow?
2026-03-02 | Monday |  |  | Research CNE adhacent companies
2026-03-02 | Monday |  |  | Email accountability my KPI goals for the week (and my new process)
|  |  |  | Switch microsoft to thegrantscout? | Marketing/Visibility
Beta Client Work
Planning & Accountability
|  |  |  | Update CRM to show weekly stats and results | Sales Analysis
|  |  |  | Get an AI notetaker for teams meetings | Sales Prep
|  |  |  | Get an email if someone fills out the form | Sales Prep
|  |  |  | Reach out to Tech Stack | Direct Sales Actions
|  |  |  | Set up email campaign to nonprofits | Sales Prep
|  |  |  | Set up email campaign to foundations | Sales Prep
Get additional 990 data for the database
Send 5 Beta reports
Build pipeline test harness
Call foundation leads
Call 100 nonprofit prospects
Migrate database to supabase
Consolidate report generation scripts/prompting

## Sheet3
| Linkedin Connection Requests | Accepted Requests | Messaged | Sent List | Scheduled Meeting | Called | VM | Calls Returned | Sent Email | Meeting Scheduled
2026-02-23 | 142 |  |  |  |  | 10

## Sheet1
Patient Safety Movement Foundation | PSMF
Retirement Housing Foundation | RHF
SNS | SNS
Horizons National Student Enrichment Program Inc. | HN
Friendship Circle SD INC | FC

## Beta Leads (hidden)
Beta Group
Status | Beta Group | Company | Contact Name | State | Contact Date | Phone Number | Contact Email | Report Email | Website | Contact Method | Notes | Follow Up Date
1. Gave feedback | BG1 | Senior Network Services | Mariam | CA | 2024-11-14 | 831-216-6132 | mariama@seniornetworkservices.org |  | https://seniornetworkservices.org/ | Cold Call | 11-14-2025 - Called, left VM. She called back and said she consults other nonprofits on doing this, asked how we're different than grant watch, and said she wants to be able to opt out in case she gets too many emails(concerned about getting too many emails)
1. Gave feedback | BG1 | Patient Safety Movement Foundation | Consuelo | CA | 2025-11-05 | 9492307588 | info@psmf.org |  | https://PSMF.ORG | Cold Call | 11/5/2025 - info@psmf.org - consuelo answered and said that michael wasn't available but that it sound interesting.
1. Gave feedback | BG1 | Anaheim Memorial Manor Inc | Andy | CA | 2025-11-14 | 5622575100 | andy.do@rhf.org |  |  | Cold Call | 11/14/2025 - Asked to talk to the person that does grant acquisition. Got transferred to Andy. He said sure might as well. Sent him the email with the survey while on the call. He said he'd fill it out after passing it through IT to make sure the link is safe.
2. Recieved Report | BG1 | Ka Ulukoa | Lee Lamb | HI | 2025-11-12 | (808) 741-1276 | lamb@kaulukoa.org |  | https://www.kaulukoa.org/ | Cold Email | 11/12/2025 - He responded: "This email address is fine, admin@kaulukoa.org. Thanks."
2. Recieved Report | BG1 | Arborbrook Christian Academy | Derek Durst | NC | 2025-11-12 | (704) 821-9952 | derek.durst@arborbrook.org |  | https://www.arborbrook.org/ | Cold Email | 11/12/2025 - "Yes, I would be interested. This is the best email ". As in use this email to send the alerts
3. Filled out questionnaire | BG2 | Horizons National | Alex Hoffmaster | PA | 2025-12-01 | 267-990-9634 | ahoffmaster@horizonsnational.org | info@horizonsnational.org | https://www.horizonsnational.org/ | Cold Email | 11/24/2025 - Sent cold email and he scheduled a zoom call 11/25/2025 - Zoom call notes:national office of out of school K-8 programs. 6 week summer program. Enrichment activities. Students are with them for 6 week program. $43 decentralized network. National funding(his team focuses on) program quality and expanding network (to add 2-3 sites a year. Also middle of the road funders (multiple geographies). hyperlocal funding (locally based foundations in the community where the sites are) Direct fundraising goal (cash needed to operate) indirect fundraising (getting resources to build or learn etc.) Want to identify opportunities for all three(instead of just looking for funds for the national office. Donors search on the individual side (pooled publicly available info - who would be the right one) . from strategy perspective a lot of upside to working with family foundations. have had a lot of success working with family foundations (receptive to cause and in mission). Which foundations have you received from in the last year? 12/1/2025 - He filled out the onboarding form and is ready for a report
4. Interested |  | Catalina Island Conservancy | Kristine Partridge | CA | 2025-11-07 | 562-437-8555 | kristinepartridge@me.com |  | https://catalinaconservancy.org/ | Linkedin | 11/10/2025 - Said she wouldn't mind getting the emails.
4. Interested |  | Sonoma County Farm Bureau | Brooke | CA | 2025-11-06 | 7075445575 | Brooke@sonomafb.org |  | https://WWW.SONOMAFB.ORG | Cold Call | 11/6/2025 - Talked to Brooke, she gave me her email and said to send an email to her and then she'll forward it to Dayna who'll be the one that decides. Brooke@sonomafb.org 11/12/2025 - Also got put in spam - she said to send over my linkedin and she'd forward all three emails/info for Dayna to look at and decide if they want to join. She asked if I was with a company and I explained a bit about my background and how I'm testing out something I've built on the side.
4. Interested |  | Children Today Inc | Fernanda | CA | 2025-11-06 | 5629978800 | Alexis@childrentoday.org |  | https://WWW.CHILDRENTODAY.ORG | Cold Call | 11/6/2025 - Fernanda said she'd let Alexis know I called. Alexis@childrentoday.org. 11/12/2025 - Alexis answered and said that Elia is the right person to talk to and gave me her email: elia@childrentoday.org.
4. Interested |  | Friendship Circle of San Diego | Rabbi Yossi |  | 2025-11-14 | 9294137405 | rabbiyossi@friendshipsd.org |  | https://www.friendshipsd.org/ | Cold Call | 11/12/2025 - He called back and said he was interested. I texted him the form but haven't heard back from him 12/3/2025 - Texted backa nd said he would fill out th eform tomorrow
5. Engaged |  | Highland Lakes Family Crisis Center |  | TX | 2025-12-01 |  | hlfcc@hlfcc.org | hlfcc@hlfcc.org | https://www.hlfcc.org/ | Cold Email | 11/21/2025 - Sent cold email 12/1/2025 - They emailed back: Hi, This email works. What exactly will you do for the organization?Thank you
4. Interested |  | VetsBoats | Terry Moran | CA | 2025-12-02 |  | office@bnotshirah.org | office@bnotshirah.org | https://www.vetsboats.org/ | Linkedin | 11/7/2025 - Connected on Linkedin and said he'd like to chat sometime 12/1/2025 - Scheduled a meeting for 12/4/2025 12/4/2025 - Chatted with him - he built the nonprofit and is working on expanding nationwide. They just brought on a development guy named Matt. He was interested in what we're doing and said he'd set up a meeeting with matt. I pitched him $99 a month for a monthly report. He sent me this llink to learn more about them: https://www.vetsboats.org/post/vetsboats-foundation-our-why
5. Engaged |  | Shirah Elementary |  | NJ | 2025-12-01 |  | office@bnotshirah.org | office@bnotshirah.org | https://www.bnotshirah.org/ | Cold Email | 11/24/2025 - Thank you for reaching out.Our email is the one you already have - office@bnotshirah.org. Please send us the document you use to survey. Thanks! 12/1/2025 - Haven't heard back, sent follow up email
6. Check back later |  | Bikur Cholim | Lucky | CA | 2025-11-05 | 3238521900 | info@bikurcholim.net |  | https://WWW.BIKURCHOLIM.NET | Cold Call | 11/5/2025 - Lucky - Director. Needs Review, how do they connect to it etc(said make the email as detailed as possible so they can look into it. - info@bikurcholim.net. 11/12/2025 - Working through a lot right now (technical challenges etc with other things(I guess they just migrated all of their systems to mac book) - Let them know when we launch, and then reach out again in six months when they're probably more settled and they'll be able to focus on it. REACH OUT WHEN LAUNCHING AND IN SIX MONTHS(5/12/2025) | 2025-05-12

## Sheet2 (hidden)
Status
1. Gave feedback
2. Recieved report
3. Filled out questionnaire
4. Interested
5. Engaged
6. Check back later
7. Not Interested